# Roadmap for the SAFMC Snapper-Grouper MSE Project

Planned Meeting Schedule and Key Milestones

\* Meetings with the Technical Advisory Group to be held as needed throughout the project

|  |  |  |
| --- | --- | --- |
| **Date** | **Meeting/Milestone** | **Key Topics/Outcomes** |
| 1 July 2022 | Commencement of Project |  |
| 18 – 20 October 2022 | Advisory Panel | * Introduction to MSE project * Initial discussion of operating models, potential management procedures, and performance metrics |
| 25 October 2022 | SSC | * Introduction to MSE project * Initial discussion of operating models, potential management procedures, and performance metrics |
| 15 November 2022 | Progress Report 1 | * Development of preliminary two-species operating model to demonstrate the multi-species MSE |
| 6 March 2023 | SAFMC Council | * Introduction to MSE project * Initial discussion of operating models, potential management procedures, and performance metrics |
| 17 April 2023 | SSC (socio-economic meeting) | * If required, discuss socio-economic questions with the SSC |
| 25 – 27 April 2023 | Advisory Panel | * Presentation of initial reference set of operating models * Presentation of initial candidate management procedures and preliminary results * Discussion of key system uncertainties and potential management options * Public Scoping Session |
| 15 May 2023 | Progress Report 2 | * Development of initial reference set of operating models that span key uncertainties * Development of potential quantitative performance metrics * Initial development and evaluation of candidate management procedures (CMP) |
| October 2023 | Advisory Panel | * Present revised operating models and management procedures based on feedback from April meeting * Presentation of results of initial evaluation of the CMPs * Discussion of additional uncertainties |
| 24 – 26 October 2023 | SSC | * Update on MSE progress and discussion of initial results * Discussion of management options and performance metrics |
| 15 November 2023 | Progress Report 3 | * Finalize development of management procedures * Conduct initial robustness testing/sensitivity analysis of the CMPs * Compile results for presentation in an online interactive app * Develop and host interactive app for reviewing results * Revise operating models and CMPs based on feedback from the AP and SSC |
| 4 – 8 December 2023 | Council | * Update on MSE progress and discussion of initial results * Discussion of management options and performance metrics |
| 4 – 8 March 2024 | Council | * Alternative date for row above |
| April 2024 | SSC | * Review of final model |
| April 2024 | Advisory Panel | * Presentation of MSE results and discussion to finalize OMs, CMPs, and performance metrics |
| 10 – 14 June 2024 | Council | * Presentation of MSE results and discussion to finalize OMs, CMPs, and performance metrics |
| 30 June 2024 | Final Report | * Finalize MSE testing of CMPs for reference and robustness operating models * Conduct cost-of-current uncertainties analysis * Update Shiny app * Draft peer-review paper * Submit final report |